## Feuil1
ETU001844 | RAMANANTSALAMA Dirk Tony
Repo git: https://github.com/tonymushah/evaluation-juillet-2024
Catégorie | Taches | Type | Qui | Estimation | Temps passé | Reste à faire | Avancement
Mise en place environment | Setup Base Postgres |  |  | 5 | 5 | 0 | 100%
Mise en place environment | Setup Diesel ORM |  |  | 5 | 5 | 0 | 100%
Mise en place environment | creation du Diesel-schema crate |  |  | 2 | 2 | 0 | 100%
Migration | create_reset_db |  |  | 2 | 2 | 0 | 100%
Migration | create_region |  |  | 2 | 2 | 0 | 100%
Migration | create_proprietaire |  |  | 2 | 2 | 0 | 100%
Migration | create_type_bien |  |  | 2 | 2 | 0 | 100%
Migration | create_type_bien_commission |  |  | 2 | 2 | 0 | 100%
Migration | create_v_type_bien_commission |  |  | 4 | 4 | 0 | 100%
Migration | create_bien |  |  | 2 | 2 | 0 | 100%
Migration | create_loyer_par_mois |  |  | 2 | 2 | 0 | 100%
Migration | create_v_bien |  |  | 2 | 2 | 0 | 100%
Migration | create_client |  |  | 2 | 2 | 0 | 100%
Migration | create_location |  |  | 2 | 2 | 0 | 100%
Migration | create_payement |  |  | 2 | 2 | 0 | 100%
Migration | create_v_location_payement |  |  | 2 | 2 | 0 | 100%
Migration | create_v_location_payement_reste |  |  | 5 |  | 5 | 0%
Migration | create_v _location_payement_commission |  |  | 5 |  | 5 | 0%
Models | reset db function |  |  | 2 | 2 | 0 | 100%
proto Admin | Service Auth |  |  | 2 | 2 | 0 | 100%
proto Admin | rpc login |  |  | 2 | 2 | 0 | 100%
proto Admin | service Comptes |  |  | 2 | 2 | 0 | 100%
proto Admin | rpc chiffre_affaire |  |  | 1 | 1 | 0 | 100%
proto Admin | rpc gains |  |  | 1 | 1 | 0 | 100%
proto Proprietaire | service Auth |  |  | 2 | 2 | 0 | 100%
proto Proprietaire | rpc login |  |  | 1 | 1 | 0 | 100%
proto Proprietaire | rpc signup |  |  | 1 | 1 | 0 | 100%
proto Proprietaire | service Biens |  |  | 2 | 0 | 2 | 0%
proto Proprietaire | rpc listBien |  |  | 1 |  | 1 | 0%
proto Proprietaire | rpc getBien |  |  | 1 |  | 1 | 0%
proto Proprietaire | service Comptes |  |  | 1 | 0 | 1 | 0%
proto Proprietaire | rpc chiffre_affaire |  |  | 1 |  | 1 | 0%
proto Client | service Auth |  |  | 2 | 2 | 0 | 100%
proto Client | rpc login |  |  | 1 | 1 | 0 | 100%
proto Client | rpc signup |  |  | 1 | 1 | 0 | 100%
proto Client | service Payement |  |  | 2 | 2 | 0 | 100%
proto Client | rpc loyers |  |  | 1 | 1 | 0 | 100%
proto Client | rpc loyers_paye |  |  | 1 | 1 | 0 | 100%
Mise en place environment | creation du protobuf-types crate |  |  | 5 | 5 | 0 | 100%
Mise en place environment | Codegen typescript |  |  | 5 | 5 | 0 | 100%
Proto integration Admin | Mise en place token |  |  | 10 |  | 10 | 0%
Proto integration Admin | Service Auth |  |  | 5 | 5 | 0 | 100%
Proto integration Admin | rpc login |  |  | 5 | 5 | 0 | 100%
Proto integration Admin | service Comptes |  |  | 10 | 0 | 10 | 0%
Proto integration Admin | rpc chiffre_affaire |  |  | 5 |  | 5 | 0%
Proto integration Admin | rpc gains |  |  | 5 |  | 5 | 0%
Proto integration Proprietaire | Mise en place token |  |  | 5 | 5 | 0 | 100%
Proto integration Proprietaire | service Auth |  |  | 10 | 5 | 5 | 50%
Proto integration Proprietaire | rpc login |  |  | 5 | 5 | 0 | 100%
Proto integration Proprietaire | rpc signup |  |  | 5 |  | 5 | 0%
Proto integration Proprietaire | service Biens |  |  | 10 | 0 | 10 | 0%
Proto integration Proprietaire | rpc listBien |  |  | 5 |  | 5 | 0%
Proto integration Proprietaire | rpc getBien |  |  | 5 |  | 5 | 0%
Proto integration Proprietaire | service Comptes |  |  | 5 | 0 | 5 | 0%
Proto integration Proprietaire | rpc chiffre_affaire |  |  | 5 |  | 5 | 0%
Proto integration Client | Mise en place token |  |  | 5 |  | 5 | 0%
Proto integration Client | service Auth |  |  | 10 | 5 | 5 | 50%
Proto integration Client | rpc login |  |  | 5 | 5 | 0 | 100%
Proto integration Client | rpc signup |  |  | 5 |  | 5 | 0%
Proto integration Client | service Payement |  |  | 4 | 0 | 4 | 0%
Proto integration Client | rpc loyers |  |  | 2 |  | 2 | 0%
Proto integration Client | rpc loyers_paye |  |  | 2 |  | 2 | 0%
Frontend Admin | Login |  |  | 5 | 5 | 0 | 100%
Frontend Admin | Page acceuill |  |  | 5 | 5 | 0 | 100%
Frontend Admin | Chiffre d’affaire componnent |  |  | 5 | 5 | 0 | 100%
Frontend Admin | Gains par mois componnent |  |  | 5 | 5 | 0 | 100%
Frontend Proprietaire | Login |  |  | 5 | 5 | 0 | 100%
Frontend Proprietaire | inscription |  |  | 5 | 5 | 0 | 100%
Frontend Proprietaire | Listes des biens |  |  | 5 | 5 | 0 | 100%
Frontend Proprietaire | Chiffre d’affaire |  |  | 5 | 5 | 0 | 100%
Frontent Client | Login |  |  | 5 | 5 | 0 | 100%
Frontent Client | inscription |  |  | 5 | 5 | 0 | 100%
Frontent Client | Page loyer |  |  | 5 | 5 | 0 | 100%
Frontent Client | Loyer filter componnent |  |  | 5 | 5 | 0 | 100%
Integration Admin | Mise en place token |  |  | 5 | 5 | 0 | 100%
Integration Admin | Login |  |  | 2 | 2 | 0 | 100%
Integration Admin | Page acceuill |  |  | 2 | 2 | 0 | 100%
Integration Admin | Chiffre d’affaire componnent |  |  | 2 | 2 | 0 | 100%
Integration Admin | Gains par mois componnent |  |  | 2 | 2 | 0 | 100%
Integration Proprietaire | Mise en place token |  |  | 2 | 2 | 0 | 100%
Integration Proprietaire | Login |  |  | 3 | 3 | 0 | 100%
Integration Proprietaire | inscription |  |  | 3 |  | 3 | 0%
Integration Proprietaire | Listes des biens |  |  | 3 | 3 | 0 | 100%
Integration Proprietaire | Chiffre d’affaire |  |  | 3 | 3 | 0 | 100%
Integration Client | Mise en place token |  |  | 2 | 2 | 0 | 100%
Integration Client | Login |  |  | 2 | 2 | 0 | 100%
Integration Client | inscription |  |  | 2 | 2 | 0 | 100%
Integration Client | Page loyer |  |  | 3 | 3 | 0 | 100%
Integration Client | Loyer filter componnent |  |  | 3 |  | 3 | 0%
Import donnees backend | bien imports |  |  | 10 | 20 | 0 | 100%
Import donnees backend | location imports |  |  | 10 | 20 | 0 | 100%
Import donnees backend | commission imports |  |  | 10 | 20 |  | 100%
proto Admin | Service Import |  |  | 4 | 4 | 0 | 100%
proto Admin | rpc bien |  |  | 2 | 2 | 0 | 100%
proto Admin | rpc location |  |  | 2 | 2 | 0 | 100%
Frontend Admin | Page import |  |  | 5 |  | 5 | 0%
Proto integration Admin | Service Import |  |  | 10 | 0 | 10 | 0%
Proto integration Admin | rpc bien |  |  | 5 |  | 5 | 0%
Proto integration Admin | rpc location |  |  | 5 |  | 5 | 0%
Integration Admin | Page import |  |  | 2 |  | 2 | 0%
proto Admin | Service Location |  |  | 10 | 10 | 0 | 100%
proto Admin | rpc NewLocation |  |  | 2 | 2 | 0 | 100%
proto Admin | rpc ListBien |  |  | 4 | 4 | 0 | 100%
proto Admin | rpc ListClient |  |  | 4 | 4 | 0 | 100%
proto Client | Service payement |  |  | 1 | 1 | 0 | 100%
proto Client | rpc FairePayement |  |  | 1 | 1 | 0 | 100%
proto Admin Integration | Service Location |  |  | 10 | 10 | 0 | 100%
proto Admin Integration | rpc NewLocation |  |  | 2 | 2 | 0 | 100%
proto Admin Integration | rpc ListBien |  |  | 4 | 4 | 0 | 100%
proto Admin Integration | rpc ListClient |  |  | 4 | 4 | 0 | 100%
proto Client Intergration | Service payement |  |  | 1 | 1 | 0 | 100%
proto Client Intergration | rpc FairePayement |  |  | 1 | 1 | 0 | 100%
Frontend Admin | Form New Location |  |  | 10 | 10 | 0 | 100%
Frontend Client | Page payer location |  |  | 10 | 10 | 0 | 100%
Integration Admin | Form New Location |  |  | 5 |  | 5 | 0%
Integration Admin | Page payer location |  |  | 5 |  | 5 | 0%
|  |  |  | 454 | 332 | 152 | 68.6%
*Valeur en Minutes
Estimation: | 454
Temps passé | 332
Reste à faire | 152
par défaut : Reste à faire = Estimation - Temps Passé